## Slide 1: Software Project Management
Dr. Nguyen Hai Quan

## Slide 2: Agenda
Why SCRUM?
What is SCRUM?
Some terms
SCRUM Meetings
Sprint
Estimation
Product backlog
Sprint backlog
Whiteboard and Post-It’s
Burn-down charts
SCRUM Process

## Slide 3: Why SCRUM?
Frequent deliveries of completed functionality
Small iterations = easier to adapt to change
Customer involvement => customer satisfaction
Deliver business value - Most important requirements are done first, prioritized frequently
Visible progress = predictable progress
Continuous improvement
Helps focus and motivate team

## Slide 4: What is SCRUM?
term from rugby
a process with a set of roles and practices for agile development
iterative = timeboxed (sprints)
incremental = features added incrementally
continuous process improvements = retrospectives

## Slide 5: Some terms
Team viewpoint
  Product Owner - voice of the customer
  Scrum Master - enforcer of Scrum process, facilitates (removing impediments) team to reach sprint goal
  Team - cross-functional (design, developer, test), usually 5-9 people who does the work
User viewpoint
  Users
  Stakeholders (Customers, Vendors)
  Managers

## Slide 6: SCRUM Meetings
daily standup meetings
same time, same location (punishment for tardiness)
all are welcome, but only pigs may speak
timeboxed at 15 min
questions
  What have you done yesterday?
  What will you do today?
  Do you have any problems preventing you from accomplishing your goal?
    (ScrumMaster to remove impediments)
not a progress report, not to be addressed to scrum master, but to inform each other

## Slide 7: Sprint
Timeboxed iteration
Usually 2-4 weeks
Determine sprint goal
Working functionality
  features incrementally added
  definition of done
    must decide for each task
    i.e. unit tested + demo ready

## Slide 8: Product Backlog
describes "what" will be built
managed by product owner
translates requirements into user stories
user stories = one or two sentences in language of customer
with rough estimates (in days)
with priorities (e.g.MoSCoW), reprioritized after each sprint

## Slide 9: Sprint Planning Meeting
  Timeboxed at 4 hours
  Team to negotiate with product owner what to put in sprint
  Determine the sprint goal (specific, measurable, demonstratable)
  Translate user stories into "how" a requirement is to be built

## Slide 10: Estimation
Estimate in story point or ideal days?
  Story points = relative units of effort
  Ideal days = remember the “ideal” part
Planning poker
  entire team involved (users, team member can be present)
  everyone gets a deck of cards with numbers representing the number of story points (number of cards and points to be determined)
  for each user story, everyone estimates the number of story points individually
  if a user story takes too long, break it down
  show cards at same time
  discuss discrepancies

## Slide 11: Sprint Backlog
Produced from sprint planning meetings
Task can be of the following types:
  Design tasks
  Coding tasks
  Testing tasks
  Documentation tasks
Tasks are not assigned, but signed up for
  each person is working on one task at a time
  estimate of the task adjusted daily
Tasks cannot be added, but can be removed if out of time
  velocity will be established over iterations
  velocity = the number tasks that the team can complete in one sprint

## Slide 12: Whiteboard and Post-It’s
User Story | Todo |  | In progress | To review /verify | Done
User story | Design the… (2) | Code the… (3) |  |  | 
 | Code the… (5) | Test the… (1) |  |  | 
 | Document the… (1) | … |  |  | 
User story 2 |  |  |  |  | 

## Slide 13: Burn Down Charts
Used to track progress
Sprint burndown chart
  the number of tasks left in a sprint backlog
  can go up and down (individual tasks being worked on are re-estimated per day)
Product burndown chart
  the number of requirements left
  requirements can be added or removed, and constantly prioritized

## Slide 14: SCRUM Process
create product backlog
  (product owner, customer => prioritized user stories)
create sprint backlog - sprint planning meetings
  (involves product owner, scrum master, team)
execute sprint
  daily scrum meetings
  Scrum Master to remove impediments
  progress tracked with whiteboard, burn-down charts
sprint review
  demo, invite everyone including customer
  was the sprint goal met according to customer?
sprint retrospective (continuous improvements)
    what do we want to start doing?
    what do we want to stop doing?
    what do we want to keep doing?